## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | No Dependency | snehith | 3- Completed
S1 | S1 | US-001 | Road map and model research | MUST HAVE | Google | yashwanth | 3- Completed
S2 | S2 | US-001 | Workflow and Architecture | SHOULD HAVE | W3 schools | ghousiya | 3- Completed
S2 | S2 | US-001 | Document discussion(Agile document) | SHOULD HAVE | No Dependency | joshnavi | 3- Completed
S3 | S3 | US-001 | frontend development | MUST HAVE | Versal | joshnavi, ghousiya | 3- Completed
S5 | S5 | US-001 | Backend development and model server | MUST HAVE | Render | snehith | 3- Completed
S4 | S4 | US-001 | model training | MUST HAVE | XG Boost | yashwanth | 3- Completed
S6 | S6 | US-001 | Working on model deployment | MUST HAVE | Versal | yashwanth | 3- Completed
S7 | S7 | US-001 | Project discussion Module1(frontend development & improvement) | SHOULD HAVE | React, Vite, Recharts, Axios for frontend | yashwanth, joshnavi,snehith | 3- Completed
S8 | S8 | US-001 | Project discussion module 2(Backend) | MUST HAVE | Node.js, Express.js for backend | yashwanth, joshnavi,snehith, ghousiya | 3- Completed
S9 | S9 | US-001 | project discussion module 3(model server) | MUST HAVE | Python,flask | yashwanth, ghousiya, joshnavi | 2- In Progress
S10 | S10 | US-001 | project discussion module 4(Deployment) | MUST HAVE | Versal | yashwanth, joshnavi,snehith, ghousiya | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 27 | 18 | 13 | 7 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project | 2025-08-17 | 2025-08-19 | snehith | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Road map and model research | 2025-08-20 | 2025-08-22 | yashwanth | Others | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Workflow and Architecture | 2025-08-23 | 2025-08-26 | ghousiya | Others | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Document discussion(Agile document) | 2025-08-27 | 2025-08-29 | joshnavi | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | frontend development | 2025-08-30 | 2025-09-05 | joshnavi, ghousiya | Coding | 3- Completed | 12 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Backend development and model server | 2025-09-06 | 2025-09-11 | snehith | Coding | 3- Completed | 10 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | model training | 2025-09-12 | 2025-09-15 | yashwanth | Unit Test | 3- Completed | 9 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Working on model deployment | 2025-09-16 | 2025-09-19 | yashwanth | System Test | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Project discussion Module1(frontend development & improvement) | 2025-09-21 | 2025-09-23 | yashwanth, joshnavi,snehith | Coding | 3- Completed | 12 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Project discussion module 2(Backend) | 2025-09-24 | 2025-09-26 | yashwanth, joshnavi,snehith, ghousiya | Coding | 3- Completed | 8 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 11 | project discussion module 3(model server) | 2025-09-28 | 2025-09-29 | yashwanth, ghousiya, joshnavi | Integration Test | 2- In Progress | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | project discussion module 4(Deployment) | 2025-09-30 | 2025-10-02 | yashwanth, joshnavi,snehith, ghousiya | System Test | 2- In Progress | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day-3 | Query about work flow and architecture | conducted a detail discussion with team
Sprint 1 | Day-5 | Lack of clarity in model selection | In the meeting mentor will clarify the doubts about the model selection
Sprint 2 | Day-9 | Agile template confusion | mentor will clarify the doubts in the meeting
Sprint 2 | Day-12 | confusion about finding the best framework for frontend | conducted a detail discussion with team and mentors
Sprint 2 | Day-18 | Difficulty in the backend | collaborate with team members to solve the issues
Sprint 3 | Day-20 | Query about model training | conducted a brainstorming section for the team from mentor in the meeting
Sprint 4 | Day-23 | model server problem | scheduled the meeting with team members
Sprint 5 | Day-25 | Difficulty to select deployment platform | research on best deployment platform

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 17-8-2025 | 25-8-2025 | joshnavi,ghousiya | start working on frontend part of the project | completed by doing best frontend part | modifying the frontend part for the requirements | completed the frontend of the project
2 | Sprint 3 | 28-8-2025 | 2025-05-09 | snehtih sambaraj | working on backend part | delaying to connect with frontend | working on the backend servers | completed the backend work
3 | Sprint 4 | 2025-10-09 | 18-9-2025 | yashwanth | preparing model trining of the project | delaying in the model deployment | to improve the backend | choose different deployment models
4 | sprint 5 | 22-9-2025 | 26-9-2025 | yashwanth,joshnavi,snehith | participated in the meeting for the improvements | some improvement is delaying | collaborating to complete the work quickly | worked together to complete the project